Draft Action Plan Template

September 21, 2006

### NCERA-197 Agricultural Safety and Health Research and Extension

| Objective | Action/Activity | Target dates | Status |
| --- | --- | --- | --- |
| Develop and support action groups for each of 12 priority areas. These action groups would then. | Began effort at May 10, 2006 mtg. | 10/01/05 – 9/30/10 | Ongoing |
| Identity current & present research & outreach efforts supporting 12 areas Identify current and potential resources including funding and expertise for 12 areas. | Jepsen subcommittee to develop web-based reporting system that includes factors for accomplishing 1.1 and 1.2. | Develop draft 10/31/06; final report form 11/30/06; distribute to committee with return deadline of 1/31/07; posted on web 2/28/07 |  |
| Define needs and opportunities for 12 priority areas Develop and refine research questions and outreach activities for 12 areas. | Identify team members and chair (3-5) Summarize research within past five years (3-5 pages): Introduction/Problem Statement (1/2 page) Literature Review (1-3 pages) Summary and Conclusions (list, 1/2 page) Research Questions To Be Answered or Outreach Issues to be Resolved (list, 1/2 page) Development of action plans for promoting research and/or outreach activities. May include technical sessions at conferences, journal state-of-the-art articles, specialty conferences, new resources or programs, identification of RFAs that include priority areas, etc. | 10/16/06 12/31/06 3/1/07 |  |
| Develop assessment to measure effectiveness & impact off the national agenda document. | To be measured by: Documenting actions and accomplishments of Objective 1 Inclusion of priority areas in USDA RFAs Inclusion of priority areas in NIOSH National Occupational Research Agenda (NORA) others ?? | 12/31/06 – 9/30/10 3/1/07 – 9/30/10 TBD |  |
| Develop a supportive environment for exchange of ideas, partnering, and involvement of stakeholders. | Documented by activities and accomplishments from Objectives 1 and 2. | 10/01/05 – 9/30/10 | Ongoing |