## Project Schedule
PM Lite 2.0
Project Schedule
Template
Version 1.0 • February 27, 2015
Template Description
1 Purpose
The Project Schedule Template is created to help plan and track important dates within the project.
2 How to Use
The Project Schedule Template is pre-configured to align to standard Project Management life cycle processes. There are two versions of the PM Lite 2.0 Project Schedule Template. One is a Microsoft Project and the other an Excel spreadsheet. Pick the tool that works best for your project and organization. The project schedule allows you to plug in dates, resources, and budget information. Once populated with dates and resources, key performance indicators (KPIs) such as schedule variance and % complete, can then help track the project performance.
3 Best Practice
Prepare a tentative project schedule in initiation and adjust throughout the life of the project. Baselining a project schedule should occur at the conclusion of planning but may occur in initiation and re-baselined at conclusion of planning dependent on organizations policies and project details. In an effort to capture project metrics (e.g. schedule variance) and continuously improve, all project schedules/plans should be baselined. The project schedule should be used as the single source of truth regarding project schedules, baselines, and project variances.
4 Phase Location
The PM Lite Project Schedule Template is used in the Planning Phase of the project lifecycle. The Planning Phase develops the approach and schedule for delivering the project. The triple constraint (Scope, Schedule, and Cost) is finalized in the Planning Phase. The project team is formalized and the communications plan and project deliverables are identified.
Note: The PM Lite 2.0 Project Schedule Template is customizable as you see fit, on a per project basis, meeting specific needs of the project and/or your organization’s policies. The below sections are suggestions but can be tailored as applicable.
**NOTE: Please remove this page when creating your Project Schedule**

## Tasks
TASK TABLE
ID | Active | % Complete | Name | Resource Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes |  | Official Project Start |  | 70 days? | February 11, 2014 8:00 AM | May 19, 2014 5:00 PM |  | 1 | Date the PM is assigned the Project
2 | Yes |  | Initiation |  | 5 days? | February 11, 2014 8:00 AM | February 17, 2014 5:00 PM |  | 2
3 | Yes |  | Review Business Case Request (BCR) & Pre-Project Assessment (PPA) |  | 1 day? | February 11, 2014 8:00 AM | February 11, 2014 5:00 PM |  | 3
4 | Yes |  | Review Lessons Learned Repository |  | 1 day? | February 11, 2014 8:00 AM | February 11, 2014 5:00 PM |  | 3
5 | Yes |  | Create Project Charter |  | 1 day? | February 12, 2014 8:00 AM | February 12, 2014 5:00 PM | 4 | 3
6 | Yes |  | Create Draft of Project Schedule (.mpp) & Baseline |  | 1 day? | February 13, 2014 8:00 AM | February 13, 2014 5:00 PM | 5 | 3
7 | Yes |  | Milestone: Obtain approval on Project Charter |  | 1 day? | February 14, 2014 8:00 AM | February 14, 2014 5:00 PM | 6 | 3
8 | Yes |  | Milestone: Conduct Project Kickoff |  | 1 day? | February 17, 2014 8:00 AM | February 17, 2014 5:00 PM | 7 | 3
9 | Yes |  | Planning |  | 68 days? | February 11, 2014 8:00 AM | 2014-05-16 17:00 |  | 2
10 | Yes |  | Develop Project Management Plan |  | 1 day? | February 11, 2014 8:00 AM | February 11, 2014 5:00 PM |  | 3 | (defines how project and deliverables will be managed). This is not the project schedule/timeline. This plan covers resource management, quality management, communications management, risk management, and procurement management.)
11 | Yes |  | Collect Business Requirements |  | 1 day? | February 12, 2014 8:00 AM | February 12, 2014 5:00 PM | 10 | 3
12 | Yes |  | Define Project Scope |  | 1 day? | February 13, 2014 8:00 AM | February 13, 2014 5:00 PM | 11 | 3
13 | Yes |  | Obtain Approval on Business Requirements & Scope |  | 1 day? | February 14, 2014 8:00 AM | February 14, 2014 5:00 PM | 12 | 3
14 | Yes |  | Formalize WBS/Project Schedule |  | 1 day? | February 17, 2014 8:00 AM | February 17, 2014 5:00 PM | 13 | 3
15 | Yes |  | Estimate Costs |  | 1 day? | February 18, 2014 8:00 AM | February 18, 2014 5:00 PM | 14 | 3
16 | Yes |  | Develop SOW/Plan Procurement (if applicable) |  | 60 days? | February 19, 2014 8:00 AM | May 13, 2014 5:00 PM | 15 | 3
17 | Yes |  | Approval of SOW (if applicable) |  | 1 day? | May 14, 2014 8:00 AM | May 14, 2014 5:00 PM | 16 | 3
18 | Yes |  | Obtain Approval of Schedule |  | 1 day? | May 14, 2014 8:00 AM | May 14, 2014 5:00 PM | 16 | 3
19 | Yes |  | Rebaseline Schedule & Update Project Documents |  | 1 day? | May 15, 2014 8:00 AM | May 15, 2014 5:00 PM | 18 | 3 | Requires PCR to support date changes
20 | Yes |  | Execution |  | 4 days? | May 14, 2014 8:00 AM | May 19, 2014 5:00 PM |  | 2
21 | Yes |  | Product Development |  | 4 days? | May 14, 2014 8:00 AM | May 19, 2014 5:00 PM |  | 3
22 | Yes |  | Conduct Procurements (if applicable) |  | 1 day? | May 14, 2014 8:00 AM | May 14, 2014 5:00 PM | 16 | 4
23 | Yes |  | Quality Checkpoint 1 |  | 1 day? | May 15, 2014 8:00 AM | May 15, 2014 5:00 PM | 22 | 4
24 | Yes |  | Quality Checkpoint 2 |  | 1 day? | May 16, 2014 8:00 AM | May 16, 2014 5:00 PM | 23 | 4
25 | Yes |  | Sponsor/Customer Acceptance |  | 1 day? | May 19, 2014 8:00 AM | May 19, 2014 5:00 PM | 24 | 4
26 | Yes |  | Close |  | 4 days? | February 11, 2014 8:00 AM | February 14, 2014 5:00 PM |  | 2
27 | Yes |  | Complete Procurement Closure tasks (if applicable) |  | 1 day? | February 11, 2014 8:00 AM | February 11, 2014 5:00 PM |  | 3
28 | Yes |  | Provide Stakeholder Names for Customer Satisfaction Survey |  | 1 day? | February 11, 2014 8:00 AM | February 11, 2014 5:00 PM |  | 3
29 | Yes |  | Document Lessons Learned including results from Customer Satisfaction Survey |  | 1 day? | February 12, 2014 8:00 AM | February 12, 2014 5:00 PM | 28 | 3
30 | Yes |  | Seek Sponsor and Business Owner approval to close project |  | 1 day? | February 11, 2014 8:00 AM | February 11, 2014 5:00 PM |  | 3
31 | Yes |  | Complete Project Closure Template |  | 1 day? | February 13, 2014 8:00 AM | February 13, 2014 5:00 PM | 29 | 3
32 | Yes |  | Move Project from Active to Completed on SharePoint |  | 1 day? | February 14, 2014 8:00 AM | February 14, 2014 5:00 PM | 31 | 3
33 | Yes |  | Project Formally Completed |  | 0 days | February 14, 2014 5:00 PM | February 14, 2014 5:00 PM | 26 | 1
Note on F1: To fill out the Project Schedule start by clearing out the dates under the start and finish columns, and replacing with your projects dates for the given tasks.