## P Sample
Components/Task | Dependent Components | Status | Date Start | Data Complete | Owner | Difficulty | Notes
<title of your project>
Task 1 |  | open | 2008-01-04 |  | Jennifer | Small | Use the status to toggle between different states with color coding.
Task 2 |  | code complete | 2008-01-01 | 2008-02-03 | Rich | Small
Task 3 |  | open |  |  | Mike | Medium
Task 4 |  | open | 2008-01-01 | 2008-01-31 | Jason | Large
Task 5 Integrate |  | open | 2008-01-23 |  | Petar
Monetize |  | open |  |  | Sandy
--> FIRST GOAL 1 - Write down a goal; e.g. roll-out of functionality (dependent on the above tasks/stories getting done) March 30
Component A |  | open |  |  | Arjun | Small | Do some sort of grouping if needed between tasks and component.
| Task A | open |  |  | Shiela | Medium | A good example might be in a software project where you are trying to accomplish code completion of A and it depends on a number of sub tasks.
| Task B | open |  |  | Jeff
| Task C | open |  |  | Shawn | Medium
--> NEXT GOAL 2 - Write down a goal; e.g. roll-out of functionality (dependent on the above tasks/stories getting done) March 30
Dispatcher |  | future |  |  | Arjun | Small | Use a future color code for tasks not yet scheduled.
Metrics |  | future |  |  | Shiela | Medium
IMS |  | future |  |  | Jeff
Metrics Checkin |  | future |  |  | Shawn | Medium
--> NEXT GOAL 3 - Write down a goal.; e.g. roll-out of functionality (dependent on the above tasks/stories getting done) March 30

## Projects
PROJECT NAME | Status/Notes
Q1 2008
Disaster Recovery Docs | in progress
Sample Project | in progress
On Call | in progress
20% Project | in progress
Launch of Product A | done

## Actions
Context Type: AGENDAS ANYWHERE CALLS COMPUTER ERRANDS HOME OFFICE WAITING FOR SOMEDAY/MAYBE
Subject | Due Date | Context | Notes | Status | Project Name
Design meeting schedule for Eugene, Robert, John, Thai | 2008-03-28 | @COMPUTER |  | done | Out Of Jail
Peer review for JamieD | ?? | @SOMEDAY | not needed | done
followup with Jesse on 20% project - Analytics | 2008-03-25 | @COMPUTER |  | done | 20% Project
follow-up on Disaster Recovery Document | 2008-03-28 | @AGENDA | Greg and Diana on station facing apps | done | DR
follow-up on Disaster Recovery Document | 2008-03-28 | @AGENDA | Phil on proxy | done | DR
Get internet expense bill from Cox and scan it | 2008-03-12 | @COMPUTER |  | done | Miscellaneous
submit retroactive bills for Cox and send it to google payroll | 2008-03-12 | @COMPUTER |  | done | Miscellaneous
Send expense report to accounts payable | 2008-03-14 | @ERRANDS | Make sure to send receipts | done | Miscellaneous
send email to team about SMS v2 lift off |  | @COMPUTER |  | done | On-call
Diana: backward compatability requirement from SB to TenTen (translog support) | 2008-03-10 | @AGENDAS | SB Integration with TenTen | done | Out Of Jail
Alexei: IMS pushschedule for TenTen integration | 2008-03-10 | @AGENDAS | IMS integration with TenTen | done | Out Of Jail
Alexei: Has CL approved by Richard for IMS-TenTen integration | 2008-03-10 | @AGENDAS | IMS/TenTen | done | Out Of Jail
Hani: Check if spot segments is going to be part of phase 2 | 2008-03-10 | @COMPUTER | OAV integration with TenTen | done | Out Of Jail
Create buganizer category and track open issues |  | @COMPUTER | Out of Jail hotlist created | done | Out Of Jail
Deployment checklist for radar release is dependent on SMS components going live |  | @SOMEDAY |  | done | Out Of Jail
Mike/Robert/Thai: Follow-up on IMS-AAFE front end release | 2008-03-27 | @AGENDA |  | done
follow-up with Jos on SMS response | 2008-03-26 | @COMPUTER | ask Jos to indicate mart impact on SMS | done
Summarize the SMS responses to plan for SMS dependency meeting | 2008-03-27 | @COMPUTER |  | done
Prepare for retrospective | 2008-03-27 | @COMPUTER |  | done
Schedule meeting for campaign status amongst stake holders | 2008-03-31 | @COMPUTER |  | done
retrospective summary to be sent out | 2008-04-02 | @COMPUTER |  | done
Approval Bin / Creative start restrictions design |  | @SOMEDAY |  | done | Out Of Jail
last day of scrum summary to be sent out | 2008-04-02 | @COMPUTER |  | done
send launch sequence for tenten and cms to team | 2008-04-08 | @COMPUTER |  | done
task abc to do to do to do todo | 2008-03-28 | @COMPUTER | notes | open | Project A
task abc to do to do to do todo | 2008-04-15 | @COMPUTER | notes | open | Project A
abc: task abc to do to do to do todo |  | @AGENDA | notes | open | Project A
task abc to do to do to do todo | 2008-04-15 | @COMPUTER | notes | open | Project A
task abc to do to do to do todo | 2008-04-01 | @COMPUTER | notes | open | Project B
task abc to do to do to do todo |  | @SOMEDAY | notes | open | Project B
abc: task abc to do to do to do todo |  | @AGENDA | notes | open | Project B
task abc to do to do to do todo |  | @SOMEDAY | notes | open | Miscellaneous
task abc to do to do to do todo | 2008-04-05 | @AGENDA | notes | open | Miscellaneous
task abc to do to do to do todo | 2008-04-08 | @COMPUTER | notes | open | Miscellaneous
task abc to do to do to do todo | 2008-04-09 | @COMPUTER | notes | done | Miscellaneous
abc: task abc to do to do to do todo | 2008-04-11 | @AGENDA | notes | done | Miscellaneous
abc: task abc to do to do to do todo | 2008-04-12 | @AGENDA | notes | done | Miscellaneous
task abc to do to do to do todo | 2008-04-07 | @COMPUTER | notes | open | Miscellaneous
task abc to do to do to do todo | 2008-04-17 | @COMPUTER | notes | open | Miscellaneous