## Time Management To-Do
DataShare To-Do List
Status? | Task Description | Priority H M L | Owner | Due Date | Person | Notes
Merritt
testing | Persistent URLs | H | CDL | 2012-06-19 | JAK | in stage, complete, Marisa testing
testing | Provide anonymous public access to Datashare collection | H | CDL | 2012-06-19 | MS | in stage, complete, Marisa testing, bug identified
testing | Simplify ingest process | H | CDL | 2012-06-19 | MR | in stage, ask Mark status.
in-process | Simplify ingest UI | H | CDL | 2012-06-19 | MS | in stage, tiny dependency on above
not started | update user documentation for simplified ingest | H | CDL |  | AT
testing | Distinct access rules for metadata and data | H | CDL | 2012-06-19 | MR | in stage, complete, testing
testing | Processing Dublin Core XML metadata | H | CDL | 2012-06-19 | MR | high priority, UCSF needs this to submit objects
testing | Create Merritt collection | H | CDL | 2012-06-19 | PW | in stage, complete
not started | Submit initial sample objects | H | CDL | 2012-06-19 | PW/MS | dependent on processing Dublin Core XML
not started | Service-level guidelines for UCSF | H | CDL |  | CS/AT | Carly and Adrian will work together on this
not started | User functionality to delete objects | M | CDL |  |  | confirm that this is for after our June 19th release - CONFIRMED
not started | Tool to simplify object creation and submission | M | CDL |  | AT/PW/CS | Use jquery for easy ingest… we need a group to look at this and see if it will work and the UI http://blueimp.github.com/jQuery-File-Upload/
not started | Exposure of metadata to search engines | M | UCSF |  | AC | Anirvan has some ideas about (and experience with) how to accomplish the SEO
not started | Mediated communication between consumers and providers | M | CDL | longer range |  | the solution of how to capture/ catalogue this is longer range, for now, links to email for questions
Metadata
complete | Metadata schema | H | UCSF | 2012-06-19 | PW | https://wiki.library.ucsf.edu/x/q4tEAw PW monitors
complete | Method to extract metadata from Merritt | H | CDL | 2012-06-19 | PW | Part of XTF release
testing | Tool for creating metadata | H | CDL | 2012-06-19 | PW | http://cdlib-stage.cdlib.org/services/uc3/datashare/generator_nq.html
testing | Create sample metadata records | H | UCSF | 2012-06-19 |  | https://wiki.library.ucsf.edu/x/XIZWAw
XTF Discovery tool
complete | Initial XTF prototype | H | CDL |  |  | Stylesheets at https://bitbucket.org/datashare/xtf
in-process | Beta XTF site | H | UCSF
in-process | Design XTF: logos, colors | H | UCSF
complete | Design wireframes for various pages | H | UCSF |  |  | https://wiki.library.ucsf.edu/x/3o9EAw
in-process | Implement wireframes | H | UCSF
in-process | Text for site (e.g. Help, FAQ, About) | H | UCSF/CDL |  | ARJ/CS | https://docs.google.com/document/d/1-ZEDH7o7Qy7HiZylao1GhoNgiVhWVCjZtHLuMpr3dVA/edit
Data Use Agreements
complete | Spec for DUA in Merritt | H | CDL |  | SA | spec complete. TC shared with DASHers
in-process | Implement DUA in Merritt | H | CDL |  | MS
in-process | Wording for DUAs | H | UCSF |  | ARJ | MS to get text from UCSF
not started | Customizable object-level DUA | H | CDL |  |  | An important piece for phase II
Workplan
| Assemble parts: Merritt, metadata, XTF, DUAs |  |  |  |  | Phase I
| Submit initial sample data |  |  |  |  | Phase I
| Add lab, personal information per wireframes |  |  |  |  | Phase I
| Release website |  |  |  |  | Phase I
| Develop restricted website for data submission |  |  |  |  | Phase II
| Recruit data providers |  |  |  |  | Phase II
| Production (our pieces) version of DataShare available |  |  | 2012-06-19
not started
[7 empty] | in process | in dev
delayed
[7 empty] | testing | in stage
[7 empty] | complete | in production
Use this to-do list to help you keep track of DataShare tasks that we need to complete.
Enter your own tasks, and notes to personalize the checklist for the things you need to get done.
Status?:
Use the drop down list to add the status (not started, in process, delayed, complete) for each task.
Task Description:
Write a brief description of each task.
Priority:
Enter the priority H=high M=medium L=low
Owner:
Add the name of the institution responsible for each task.
Person:
JAK (John Kunze), MS (Marisa Strong), MR (Mark Reyes), AT (Adrian Turner), PW (Perry Willett), CS (Carly Strasser), SA (Stephen Abrams)
Due Date:
Enter the Date that the task must be completed.
Dependencies:
If necessary list any task dependencies, particularly for tasks that are delayed.
Notes:
Add notes to explain yourself.