## Cost Tracking
PROJECT COST TRACKING WORKSHEET
Project Name: | Sample Refining Company |  |  | Original Contract: | 83440 | Current Contract: | 83440
Project No.: | 174 |  |  | Budgeted Cost: | 50400 | Project EAC: | 42247.62 | 69.97% | Complete (Cost Incurred Basis)
Date: | 2015-09-02 11:21 |  |  | Budgeted GM: | 33040 | Projected GM: | 41192.38 | 83.79% | Complete (Cost Committed Basis)
Project Mgr.: | P. Mangerski |  |  | Budgeted GM: | 39.6% | Projected GM: | 49.37%
Cost Code | Desctiption | Vendor | Purchase Order Number | Original Budgeted Cost | Cost Committed | Cost to Date | Freight Cost | Open P.O. Cost | Estimated Cost to Complete | Estimated Cost at Completion | Variance | P O | Recd | Paid
| Maintenance Gate Vavle | Salina Vortex | 174-003 | 950 | 749.7 | 750 | 19 | 0 | 0 | 769 | 181 | x | x
| Rotary Valve | Rotolok | 174-004 | 2300 | 2059.98 | 2059.98 | 49.21 | 0 | 0 | 2109.19 | 190.81 | x | x | x
| Feeder | Acrison | 174-002 | 4200 | 3745 | 0 | 0 | 3745 | 250 | 3995 | 205 | x | x
| Feeder Motor | Electric Motors Co. | 174-007 | 1550 | 1149.72 | 1149.72 | 0 | 0 | 0 | 1149.72 | 400.28 | x | x
| Feeder Hopper | J & J Welding | T&M | 1500 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | x | x
| Hopper Vibrator | McMaster-Carr | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x
| Solberg Intake Filter | McMaster-Carr | 174-017 | 80 | 45.83 | 45.83 | 4.29 | 0 | 0 | 50.12 | 29.88 | x | x
| Expansion Joints | Custom Adv. Conn. | 174-013 | 80 | 37.5 | 37.5 | 5.57 | 0 | 0 | 43.07 | 36.93 | x | x | x
| Wetting Cone | J & J Welding | T&M | 400 | 0 | 0 | 0 | 0 | 400 | 400 | 0 | x | x
| Eductor, 1 1/2, SS | Level & Flow | 174-012 | 610 | 513 | 513 | 8.52 | 0 | 0 | 521.52 | 88.48 | x | x
| Three-Way Process Valve | Flow-Matic, Inc. | 174-022 | 710 | 691 | 691 | 69.25 | 0 | 0 | 760.25 | -50.25 | x | x
| 1 1/2" Actuated Ball Vavle | N/A | N/A | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 510 | x | x | x
| 1 1/2" Anigav Valve | Diversified Controls | 174-016 | 270 | 306 | 306 | 7.84 | 0 | 0 | 313.84 | -43.84 | x | x
| ASCO 3-Way | Smither Equip. | 174-015 | 260 | 248.46 | 248.46 | 5.53 | 0 | 0 | 253.99 | 6.01 | x | x
| Swage-Lok Fittings & Tubing | In Stock | N/A | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | x | x | x
| Air Pressure Regulator | McMaster-Carr | N/A | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | x | x | x
| Washdown Water Regulator | ICI Cash Valve | 174-014 | 0 | 129.76 | 129.76 | 0 | 0 | 0 | 129.76 | -129.76 | x | x | x
| Pressure Gauges (One w/ Seal) | Griffith Ind. Prod. | 174-011 | 210 | 49.07 | 49.07 | 0 | 0 | 0 | 49.07 | 160.93 | x | x
| Piping & Fittings | Industrial Pipe | 174-021 | 800 | 444.37 | 444.37 | 0 | 0 | 0 | 444.37 | 355.63 | x | x
| Miscellaneous | McMaster-Carr | 174-024 | 0 | 21.72 | 21.72 | 3.43 | 0 | 0 | 25.15 | -25.15 | x | x
| Mechanical Equipment |  |  | 14790 | 10191.11 | 6446.41 | 172.64 | 3745 | 2150 | 12514.05 | 2275.95
| Control Panels | T&G Controls | 174-005 | 8000 | 8900 | 8900 | 0 | 0 | 0 | 8900 | -900 | x | x
| Elec. Design / Programming / Start-up | T&G Controls | 174-001 | 4500 | 2895 | 2895 | 0 | 0 | 0 | 2895 | 1605 | x | x
| Junction Boxes | D.H. Supply / T&G | 174-018 | 950 | 797.53 | 797.53 | 0 | 0 | 0 | 797.53 | 152.47 | x | x
| Scale / Controller / Programming | Scale Systems | 174-006 | 6600 | 6590 | 6590 | 98.07 | 0 | 0 | 6688.07 | -88.07 | x | x
| Scale Calibration / Start-up | Scale Systems | 174-023 | 500 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | x | x
| Tachometer for Feeder | Simco | 174-008 | 810 | 87.3 | 87.3 | 0 | 0 | 0 | 87.3 | 722.7 | x | x
| M-Drive | Simco | 174-008 | 1060 | 805.5 | 805.5 | 14.75 | 0 | 0 | 820.25 | 239.75 | x | x
| High Water Level Switch | Fluid Flow of GA | 174-009 | 600 | 573 | 573 | 18.5 | 0 | 0 | 591.5 | 8.5 | x | x | x
| Rotameters: Motive & Washdown | Omega | 174-010 | 920 | 895 | 895 | 22.64 | 0 | 0 | 917.64 | 2.36 | x | x | *
| Pressure Switch for Motive | Griffith Ind. Prod. | 174-011 | 270 | 229.87 | 229.87 | 7.86 | 0 | 0 | 237.73 | 32.27 | x | x
| Electrical / Instrumentation |  |  | 24210 | 21773.2 | 21773.2 | 161.82 | 0 | 500 | 22435.02 | 1774.98
| Skid Fabrication & Assembly | J & J Welding | T&M | 4000 | 0 | 0 | 0 | 0 | 3000 | 3000 | 1000 | x | x
| Skid Electrical Work | Action Electric | T&M | 3000 | 0 | 0 | 0 | 0 | 1200 | 1200 | 1800 | x | x
| Fabrication Subcontracts Total |  |  | 7000 | 0 | 0 | 0 | 0 | 4200 | 4200 | 2800
| Freight To Jobsite | Truckers Express | 174-025 | 3000 | 2265 | 173 | 0 | 2092 | 0 | 2265 | 735 | x | x
| Travel Expenses - Local | Expense Reports | N/A | 1000 | 833.55 | 833.55 | 0 | 0 | 0 | 833.55 | 166.45 | x | x
| Travel Expenses - Jobsite | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x
| Drawings / Reproduction / FedEx | Misc. | N/A | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | x | x
| Other Subtotal |  |  | 4400 | 3098.55 | 1006.55 | 0 | 2092 | 0 | 3098.55 | 1301.45
| Project Total |  |  | 50400 | 35062.86 | 29226.16 | 334.46 | 5837 | 6850 | 42247.62 | 8152.38